## Sheet1
Task | 2024 | [8 empty] | 2025
| Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Berlin Research Placement | bar: 2024 Apr to 2024 May
Project 1a: Fusilli with MND - AND | bar: 2024 Jun to 2024 Aug
Project 1b: Fusilli with PPMI, ADNI, CXR | bar: 2024 Jun to 2024 Aug
Writing paper | bar: 2024 Aug to 2024 Sep
Project 2: Effect of brain MRI preprocessing | bar: 2024 Oct to 2024 Dec
Writing paper | bar: 2024 Dec to 2025 Jan
Project 3a: Prognosis definition sensitivity analysis | bar: 2025 Feb to 2025 Apr
Project 3b: Adding spinal cord data | bar: 2025 Feb to 2025 Apr
Project 3c: Adding radiological report data | bar: 2025 Feb to 2025 Apr
Writing paper | bar: 2025 Apr to 2025 May
Thesis writing | bar: 2025 May to 2025 Sep